## Sheet1
sprint No. | tasks | starting time | ending time | responsible | total time of task | percent complete | total time of sprint | Scrum master
sprint 1 registration | set up environment (android and photoshop) | 2018-03-01 | 2018-02-03 | Khalid | 1 day | 100% | 7 days | Farah
|  |  |  | Mennah | 1 day | 100%
|  |  |  | Farah | 1 day | 100%
|  |  |  | Malak | 1 day | 100%
|  |  |  | Abd Alhamid | 1 day | 100%
|  |  |  | Abd Alrahman | 1 day | 100%
| splash screen | 2018-03-02 | 2018-03-04 | Khalid | 2 days
| analysis | 2018-03-02 | 2018-03-02 | Farah | 3hrs
| design | 2018-03-02 | 2018-03-03 | Malak | 3hrs
| implementation of design | 2018-03-03 | 2018-03-03 | Abd Alrahman | 3hrs
| implementation of code | 2018-03-04 | 2018-03-04 | Mennah | 3hrs
| test | 2018-03-04 | 2018-03-04 | Abd Alhamid | 3hrs
| registration view | 2018-03-04 | 2018-03-06 |  | 2 days
| analysis | 2018-03-04 | 2018-03-04 | abdulrahman | 5hrs
| scetsh and wireframe | 2018-03-04 | 2018-03-04 | abdulhamid | 3hrs
| design | 2018-03-04 | 2018-03-05 | mennah | 5hrs
| implementation of design | 2018-03-05 | 2018-03-05 | khalid | 2hrs
| login button backend imp | 2018-03-05 | 2018-03-05 | farah | 5hrs
| login button test | 2018-03-05 | 2018-03-06 | malak | 2hrs
| signup button implementation | 2018-03-06 | 2018-03-06 | mennah | 2hrs
| sign up view | 2018-03-06 | 2018-03-08 |  | 2 days
| analysis | 2018-03-06 | 2018-03-06 | abdulrahman | 5hrs
| scetsh and wireframe | 2018-03-06 | 2018-03-06 | khalid | 3hrs
| design | 2018-03-06 | 2018-03-07 | malak | 5hrs
| implementation of design | 2018-03-07 | 2018-03-07 | farah | 2hrs
| implementation of data | 2018-03-07 | 2018-03-08 | mennah | 5hrs
| signup button backend imp | 2018-03-08 | 2018-03-08 | malak | 5hrs
| signup button test | 2018-03-08 | 2018-03-08 | abdulhamid | 2hrs
sprint 2 Home page | home page view | 2018-03-12 | 2018-03-17 |  | 5 days |  | 14 days | Mennah
| analysis | 2018-03-12 | 2018-03-12 | abdulrahman | 5hrs
| scetsh and wireframe | 2018-03-12 | 2018-03-12 | abdulhamid | 3hrs
| design | 2018-03-12 | 2018-03-13 | malak | 6hrs
| implementation of design | 2018-03-13 | 2018-03-13 | malak | 6hrs
| logout button design | 2018-03-13 | 2018-03-14 | mennah | 2hrs
| logout button implementation | 2018-03-14 | 2018-03-14 | khalid | 2hrs
| logout button backend imp | 2018-03-14 | 2018-03-15 | farah | 5hrs
| logout button test | 2018-03-15 | 2018-03-16 | abdulrahman | 5hrs
| profile button implementation | 2018-03-16 | 2018-03-17 | mennah | 2hrs
| profile view | 2018-03-17 | 2018-03-26 |  | 6 days
| analysis | 2018-03-17 | 2018-03-17 | abdulrahman | 5hrs
| scetsh and wireframe | 2018-03-17 | 2018-03-18 | abdulhamid | 2hrs
| design | 2018-03-18 | 2018-03-18 | farah | 6hrs
| implementation of design | 2018-03-18 | 2018-03-19 | mennah | 7hrs
| implementation of data | 2018-03-19 | 2018-03-20 | mennah | 5hrs
| backend implementation | 2018-03-20 | 2018-03-21 | abdulhrahman | 7hrs
| body mass index button design | 2018-03-21 | 2018-03-21 | khalid | 3hrs
| body mass index button implementation | 2018-03-22 | 2018-03-23 | abdulhamid | 3hrs
| body mass index button test | 2018-03-23 | 2018-03-24 | farah | 2hrs
| view test | 2018-03-24 | 2018-03-26 | malak | 7hrs
sprint 3 normal person | normal person view | 2018-04-03 | 2018-04-10 |  | 1week |  | 14 days | Khalid
| analysis | 2018-04-03 | 2018-04-03 |  | 2hrs
| scetsh and wireframe | 2018-04-03 | 2018-04-04 |  | 3hrs
| design | 2018-04-04 | 2018-04-04 |  | 5hrs
| design implementation | 2018-04-04 | 2018-04-05 |  | 5hrs
| gain button design | 2018-04-05 | 2018-04-05 |  | 2hrs
| gain button implementation | 2018-04-05 | 2018-04-06 |  | 3hrs
| gain view | 2018-04-06 | 2018-04-06 |  | 2hrs
| gain view design | 2018-04-06 | 2018-04-07 |  | 3hrs
| gather tips for gain view | 2018-04-07 | 2018-04-07 |  | 7hrs
| tips implementation | 2018-04-07 | 2018-04-08 |  | 3hrs
| lose button design | 2018-04-08 | 2018-04-08 |  | 2hrs
| lose button implementation | 2018-04-08 | 2018-04-08 |  | 3hrs
| lose view | 2018-04-08 | 2018-04-08 |  | 2hrs
| lose view design | 2018-04-08 | 2018-04-09 |  | 5hrs
| gather tips for lose view | 2018-04-09 | 2018-04-09 |  | 7hrs
| tips implementation | 2018-04-09 | 2018-04-09 |  | 3hrs
| total test | 2018-04-09 | 2018-04-10 |  | 8hrs
| sports view | 2018-04-10 | 2018-04-13 |  | 3days
| analysis | 2018-04-10 | 2018-04-10 |  | 2hrs
| scetch and wireframe | 2018-04-10 | 2018-04-11 |  | 3hrs
| design | 2018-04-11 | 2018-04-11 |  | 5hrs
| implementation design | 2018-04-11 | 2018-04-12 |  | 5hrs
| gather tips for sports | 2018-04-12 | 2018-04-12 |  | 8hrs
| tips implementation | 2018-04-12 | 2018-04-12 |  | 5hrs
| gather links for videos | 2018-04-12 | 2018-04-13 |  | 8hrs
| data implementation | 2018-04-13 | 2018-04-13 |  | 4hrs
| test | 2018-04-13 | 2018-04-13 |  | 5hrs
| feedback button design | 2018-04-13 | 2018-04-16 |  | 3days
| feedback button implementation | 2018-04-13 | 2018-04-14 |  | 2hrs
| edit text implementation | 2018-04-14 | 2018-04-14 |  | 3hrs
| submit button design | 2018-04-14 | 2018-04-14 |  | 3hrs
| submit button implementation | 2018-04-15 | 2018-04-15 |  | 5hrs
| submit button backend imp | 2018-04-15 | 2018-04-16 |  | 7hrs
| notification | 2018-04-16 | 2018-04-18 |  | 2days
| notification backend imp | 2018-04-17 | 2018-04-18 |  | 1day
sprint 4 patients | diabetes patient view | 2018-04-20 | 2018-04-25 |  | 5days |  | 10 days | Abdalhamid
| analysis | 2018-04-20 | 2018-04-20 |  | 2hrs
| scetsh and wireframe | 2018-04-20 | 2018-04-20 |  | 3hrs
| design | 2018-04-20 | 2018-04-20 |  | 5hrs
| implementation of design | 2018-04-20 | 2018-04-21 |  | 3hrs
| sugar rate edit text implementation | 2018-04-21 | 2018-04-21 |  | 2hrs
| sugar rate button design | 2018-04-21 | 2018-04-21 |  | 2hrs
| sugar rate button implementation | 2018-04-21 | 2018-04-21 |  | 3hrs
| low sugar view | 2018-04-21 | 2018-04-22 |  | 5hrs
| low sugar view implementation | 2018-04-22 | 2018-04-22 |  | 5hrs
| low sugar rate tips | 2018-04-22 | 2018-04-22 |  | 5hrs
| low sugar rate system | 2018-04-22 | 2018-04-23 |  | 3hrs
| high sugar rate view | 2018-04-23 | 2018-04-23 |  | 3hrs
| high sugar rate view implementation | 2018-04-23 | 2018-04-24 |  | 5hrs
| high sugar rate tips | 2018-04-24 | 2018-04-24 |  | 2hrs
| high sugar rate system | 2018-04-24 | 2018-04-25 |  | 3hrs
| hypertension patient view | 2018-04-25 | 2018-04-30 |  | 5days
| analysis | 2018-04-25 | 2018-04-25 |  | 2hrs
| scetsh and wireframe | 2018-04-25 | 2018-04-25 |  | 3hrs
| design | 2018-04-25 | 2018-04-25 |  | 5hrs
| implementation of design | 2018-04-25 | 2018-04-25 |  | 3hrs
| pressure rate edit text implementation | 2018-04-25 | 2018-04-26 |  | 5hrs
| pressure rate button design | 2018-04-26 | 2018-04-26 |  | 3hrs
| pressure rate button implementation | 2018-04-26 | 2018-04-26 |  | 5hrs
| low pressure view | 2018-04-26 | 2018-04-27 |  | 2hrs
| low pressure view implementation | 2018-04-27 | 2018-04-27 |  | 3hrs
| low pressure tips | 2018-04-27 | 2018-04-28 |  | 5hrs
| low pressure system | 2018-04-28 | 2018-04-28 |  | 5hrs
| high pressure view | 2018-04-28 | 2018-04-29 |  | 3hrs
| high pressure view implementation | 2018-04-29 | 2018-04-29 |  | 2hrs
| high pressure tips | 2018-04-29 | 2018-04-29 |  | 3hrs
| high pressure system | 2018-04-29 | 2018-04-30 |  | 2hrs
| total test | 2018-04-30 | 2018-04-30 |  | 1day |  | 1day | Abdelrahman