## Sheet1
diabetes patient view | 10 days | sum | days | sum | done | remain
analysis | 2 | 112 | 0 | 112 | 0 | 112
sketch and wireframe | 3 |  | 1 | 101.8182 | 10 | 102
design | 5 |  | 2 | 91.6364 | 3 | 99
implementation of design | 3 |  | 3 | 81.4545 | 7 | 92
sugar rate edit text implementation | 2 |  | 4 | 71.2727 | 18 | 74
sugar rate button design | 2 |  | 5 | 61.0909 | 13 | 61
sugar rate button implementation | 3 |  | 6 | 50.9091 | 10 | 51
low sugar view | 5 |  | 7 | 40.7273 | 16 | 35
low sugar view implementation | 5 |  | 8 | 30.5455 | 15 | 20
low sugar rate tips | 5 |  | 9 | 20.3636 | 10 | 10
low sugar rate system | 3 |  | 10 | 10.1818 | 10 | 0
high sugar rate view | 3 |  | 11 | 0 | 0 | 0
high sugar rate view implementation | 5 |  |  |  | 112
high sugar rate tips | 2 |  | 10.1818
high sugar rate system | 3
hypertension patient view
analysis | 2
sketch and wireframe | 3
design | 5
implementation of design | 3
pressure rate edit text implementation | 5
pressure rate button design | 3
pressure rate button implementation | 5
low pressure view | 2
low pressure view implementation | 3
low pressure tips | 5
low pressure system | 5
high pressure view | 3
high pressure view implementation | 2
high pressure tips | 3
high pressure system | 2
total test | 1day
10