## Sheet1
normal person view | 7days | hrs | 13days | 148
analysis |  | 2 |  |  | day | sum | done | remain
sketch and wireframe |  | 3 |  |  | 0 | 148 | 0 | 148
design |  | 5 |  |  | 1 | 136.6154 | 0 | 148
design implementation |  | 5 |  |  | 2 | 125.2308 | 0 | 148
gain button design |  | 2 |  |  | 3 | 113.8462 | 5 | 143
gain button implementation |  | 3 |  |  | 4 | 102.4615 | 15 | 128
gain view |  | 2 |  |  | 5 | 91.0769 | 15 | 113
gain view design |  | 3 |  |  | 6 | 79.6923 | 19 | 94
gather tips for gain view |  | 7 |  |  | 7 | 68.3077 | 11 | 83
tips implementation |  | 3 |  |  | 8 | 56.9231 | 20 | 63
lose button design |  | 2 |  |  | 9 | 45.5385 | 20 | 43
lose button implementation |  | 3 |  |  | 10 | 34.1538 | 20 | 23
lose view |  | 2 |  |  | 11 | 22.7692 | 5 | 18
lose view design |  | 5 |  |  | 12 | 11.3846 | 8 | 10
gather tips for lose view |  | 7 |  |  | 13 | 0 | 10 | 0
tips implementation |  | 3
total test |  | 8
sports view | 3days |  |  |  |  | 11.3846
analysis |  | 2
sketch and wireframe |  | 3
design |  | 5
implementation design |  | 5
gather tips for sports |  | 8
tips implementation |  | 5
gather links for videos |  | 8
data implementation |  | 4
test |  | 5
feedback button design | 3days
feedback button implementation |  | 2
edit text implementation |  | 3
submit button design |  | 3
submit button implementation |  | 5
submit button backend imp |  | 7
notification |  | 8
notification backend imp |  | 10